## Sheet1
Team Member | Time Available (Hrs / Week) | Total | [6 empty] | PROTOTYPE |  | ALPHA
[6 empty] | AUGUST |  |  |  | SEPTEMBER
Nico | 33 | 462 | Mon - Wed 9:30 - 5 | Available online off campus days |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
Byron | 33 | 462 | Mon - Wed 9:30 - 5 | Available online off campus days | Character Art | Player Character Modelling/Sculpting/UV | Player Character Modelling/Sculpting/UV | Player Character Modelling/Sculpting/UV | NPC - villager F Sculpting/Modelling/UV | NPC - villager F Sculpting/Modelling/UV | Player Character Texturing | Player Character Texturing
Shade | 33 | 462 | Mon - Wed 9:30 - 5 | Available online off campus days |  | TikTik Modelling/Sculpting/UV | TikTik Modelling/Sculpting/UV | TikTik Modelling/Sculpting/UV | NPC - villager M Sculpting/Modelling/UV | NPC - villager M Sculpting/Modelling/UV | TikTik Texturing | TikTik Texturing
Brad | 33 | 462 | Mon - Wed 9:30 - 5 | Available online off campus days | Environment Art | Main Tree Variants | Rainbow Trees, Rock Pieces | Branches, Balete Tree | Hut Variants, Chapel | Other Tree Variants (including Rainbow), | Texturing Created Assets | Texturing Created Assets
Bonnie | 33 | 462 | Mon - Wed 9:30 - 5 | Available online off campus days |  | SEPTEMBER Week 5: Stumps, Branches; SEPTEMBER Week 6: Creating Designer Materials; SEPTEMBER Week 7: Creating Designer Materials
Caleb | 33 | 462 | Mon - Wed 9:30 - 5 | Available online off campus days | Enemy Functionality | AI Attack System(Basic Attack and tutorial) | AI Attack System (Tutorial) | AI Phase 1 | A.I Phases 1 & 2 | A.I Phase 2 | A.I Phases 2 & 3 | A.I phase 3
Alex | 33 | 462 | Mon - Wed 9:30 - 5 | Available online off campus days |  | AUGUST Week 2: AI skill Tree; AUGUST Week 3: AI Skill Tree
Patrick | 33 | 462 | Mon - Wed 9:30 - 5 | Available online off campus days | Player Functionality | Character Controls - Movement | Character Control complete | Abilities, Skill Tree | Abilities, Villager A.I. | Villager A.I. | Villager A.I | Polishing/Bug Fixing
Kosta | 33 | 462 | Mon - Wed 9:30 - 5 | Available online off campus days |  | AUGUST Week 1: Abilities, Skill Tree; AUGUST Week 2: Abilities, Skill tree
|  | 4158 |  |  | System Managers | Player Combat System | Player Combat System Complete | Dialogue/Interaction System | Dialogue/Interaction System | Save/Load System | Save/Load System | Polishing/Bug Fixing
[5 empty] | UI | Function/Setup | Function/Setup | Function/Setup |  |  | UI ART | UI ART
[5 empty] | Sound | AUGUST Week 3: TikTik Sounds; AUGUST Week 4: TikTik Sounds; SEPTEMBER Week 5: Forest Sounds; SEPTEMBER Week 7: Village and Menu Sound
[5 empty] | Level | Initial Greybox Level finalised | Greybox Level Complete, Asset Import | Asset Import | Asset import | Asset Import | Asset Import | Asset Import
[8 empty] | Particle Effects | Lighting and aprticle effects | Lighting and particle Effects |  | Particle Effects
[5 empty] | Animation | AUGUST Week 4: Player Character Animations; SEPTEMBER Week 5: Player Character Animations; SEPTEMBER Week 6: Player Character Animations; SEPTEMBER Week 7: NPC Animations
[9 empty] | TikTik Animations | TikTik Animations | TikTik Animations | TikTik Animations
[5 empty] | Testing |  |  | Functionality Testing | Functionality Testing | Functionality Testing | Content Testing | Content Testing
[5 empty] | Redesign | SEPTEMBER Week 5: As needed based on testing; SEPTEMBER Week 6: As needed based on testing; SEPTEMBER Week 7: As needed based on testing
[5 empty] | Scrums | AUGUST Week 3: Sprint Review; SEPTEMBER Week 6: Sprint Review
[8 empty] | BETA |  |  |  | MASTER
[7 empty] | OCTOBER |  |  |  | NOVEMBER
[6 empty] | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
[5 empty] | Character Art | NPC Texturing | NPC Texturing | Polishing | Polishing | Polishing | Polishing | Polishing
[5 empty] | Environment Art | Modelling and Texturing Flora | Assist with particle Systems | Assist With Particle Systems | Assist with particle systems | Minor Polish | Minor Polish | Minor Polish
[6 empty] | Adding to Trees |  |  | Stretch Time for any issues/fixup
[5 empty] | Enemy Functionality | Combo Attack System | Combo Attack System | Polishing | Polishing | Polishing | Polishing | Polishing
[5 empty] | Player Functionality | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing
[5 empty] | System Managers | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing | Polishing/Bug Fixing
[5 empty] | UI | UI ART | Polishing | Polishing | Polishing | Polishing | Polishing | Polishing
[5 empty] | Sound | Polishing | Polishing | Polishing | Polishing | Polishing | Polishing | Polishing
[5 empty] | Level | Asset Import | Asset Import | Asset Import | Polishing | Polishing | Polishing | Polishing
[6 empty] | Lighting and Particle Effects | Lighting and particle Effects
[5 empty] | Animation | Player Character and NPC Polish | Player Character Polish | Player Character Polish | Player Character Polish | Polishing | Polishing | Polishing
[6 empty] | TikTik Animations | TikTik Animations | Polishing | Polishing | Polishing | Polishing | Polishing
[5 empty] | Testing | Content Testing | Content Testing | Content Testing | Content Testing | Content Testing | Final Testing | Final Testing
[5 empty] | Redesign | As needed based on testing | As needed based on testing | As needed based on testing | As needed based on testing | As needed based on testing | As needed based on testing | As needed based on testing
[5 empty] | Scrums | OCTOBER Week 9: Sprint Review