## Assets List & Time Estimates
ENVIRO ART | Time Est. Hrs | 224 | CHAR ART | Time Est. Hrs | 372 | PROGRAMMING | Time Est. Hrs | 615 | UI | Time Est. Hrs | 116 | SOUND | Time Est. Hrs | 124 | LEVEL | Time Est. Hrs | 280 | NARRATIVE | Time Est. Hrs | 120 | ANIMATION | Time Est. Hrs | 95 | TESTING | Time Est. Hrs | 52 | TOTAL | Time Est. Hrs | 1998
[28 empty] | Add 10% Redesign | 2197.8
Forest Assets | 154 |  | Tik Tik | 174 |  | Tik Tik | 190 |  | Function/Setup | 44 |  | Forest | 12 |  | Level Design | [5 empty] | Tik Tik | 40 |  | Basic Functionality | 10 |  |  | Add 30% Buffer | 2857.14
Tree 1 Variant 1 | 5 |  | Sculpting | 72 |  | A.I (Phase 1) | 40 |  | Player health | 2 |  | Ambience | 4 |  | Greybox | 50 |  | Villager Dialogue | 50 |  | Idle | 3 |  | Testing Plan | 2
Tree 1 Variant 2 | 5 |  | Modelling | 24 |  | A.I (Phase 2) | 20 |  | Player resource | 2 |  | Wildlife sounds | 3 |  | Level Draft | 20 |  | Character Backstory | 20 |  | Walking | 5 |  | Testing | 5
Tree 1 Variant 3 | 6 |  | Rigging | 26 |  | A.I (Phase 3) | 20 |  | Abilities | 3 |  | Ambush music | 3 |  | Asset Implementation | 70 |  | Objective Dialogue | 30 |  | Running | 5 |  | Analysis | 3
Tree 2 Variant 1 | 5 |  | UVing | 12 |  | A.I (Tutorial) | 20 |  | Bestiary | 4 |  | Spirit tree chimes | 2 |  | Particle Systems | 70 |  | Lore/Mythology | 20 |  | Stagger | 4
Tree 2 Variant 2 | 5 |  | Baking | 4 |  | Abilities/Skill Tree | 20 |  | Pause Menu | 3 |  |  |  |  | Lighting | 70 |  |  |  |  | Death | 6 |  | Alpha | 12
Tree 3 Variant 1 | 5 |  | Texturing | 36 |  | Combo Attack System | 20 |  | Main Menu | 4 |  | Village | 9 | [7 empty] | Lunge attack | 3 |  | Testing Plan | 3
Tree 3 Variant 2 | 5 |  |  |  |  | Bug Fixing | 50 |  | Skill Tree | 5 |  | Ambience | 3 | [7 empty] | Tongue lash | 3 |  | Testing | 5
Tree 3 Variant 3 | 5 |  | Player Character | 102 |  |  |  |  | Settings | 10 |  | Calm music | 3 | [7 empty] | Wing shield | 2 |  | Analysis | 4
Tree 4 Variant 1 | 5 |  | Sculpting | 20 |  |  |  |  | Dialogue | 5 |  | Village sounds | 3 | [7 empty] | Scream | 3
Tree 4 Variant 2 | 5 |  | Modelling | 20 |  | Player | 150 |  | Inspection | 4 | [10 empty] | Regenerating | 2 |  | Beta | 14
Tree 4 Variant 3 | 5 |  | Rigging | 25 |  | Character Controls | 50 |  | Enemy health | 2 |  | Menus | 6 | [7 empty] | Dodge | 4 |  | Testing Plan | 4
Tree 1 stump | 3 |  | UVing | 8 |  | Abilities/Skill Tree | 50 |  |  |  |  | Music | 4 | [7 empty] | Melee swipe 1 |  | 4 | Testing | 5
Tree 2 stump | 3 |  | Baking | 4 |  | Bug Fixing | 50 |  | Art | 72 |  | Button sounds | 2 | [7 empty] | Melee swipe 2 |  | 4 | Analysis | 5
Tree 3 stump | 3 |  | Texturing | 25 |  |  |  |  | Player health | 5
Tree 4 stump | 3 |  |  |  |  | NPCs | 85 |  | Player resource | 5 |  | Tik Tik | 47 | [10 empty] | Pre Master | 16
Tree Plane | 2 |  | Villager F | 47 |  | Villager A.I | 35 |  | Abilitiy Icons | 10 |  | Ticking | 3 | [7 empty] | Protagonist | 39 |  | Testing Plan | 5
Rainbow tree variant 1 | 5 |  | Sculpting | 7 |  | Bug Fixing | 50 |  | Bestiary | 10 |  | Scream | 3 | [7 empty] | Idle | 3 |  | Testing | 5
Rainbow tree variant 2 | 5 |  | Modelling | 10 |  |  |  |  | Pause menu | 5 |  | Damage taken | 3 | [7 empty] | Walking | 4 |  | Analysis | 6
Rainbow tree variant 3 | 5 |  | UVing | 4 |  |  |  |  | Main menu | 5 |  | Dodge | 3 | [7 empty] | Running | 4
Balete tree | 7 |  | Baking | 2 |  | Systems | 190 |  | Skill tree | 18 |  | Wing block | 3 | [7 empty] | Stagger | 2
Branch variant 1 | 2 |  | Texturing | 12 |  | RPG | 50 |  | Settings | 3 |  | Melee attack | 3 | [7 empty] | Death | 3
Branch variant 2 | 2 |  | Rigging | 12 |  | Combat | 20 |  | Dialogue | 5 |  | Tongue attack | 3 | [7 empty] | Melee 1 | 4
Branch variant 3 | 2 |  |  |  |  | Dialogue | 50 |  | Inspection | 3 |  | Lunge attack | 3 | [7 empty] | Melee 2 | 4
Branch variant 4 | 2 |  | Villager M | 49 |  | Save/Quick Save/Load | 20 |  | Enemy health | 3 |  | Regenerate | 3 | [7 empty] | Fireball attack | 3
Branch variant 5 | 2 |  | Sculpting | 7 |  | Bug Fixing | 50 |  |  |  |  | Retreat | 3 | [7 empty] | Earth shield | 4
Branches | 3 |  | Modelling | 10 | [7 empty] | Death | 3 | [7 empty] | Divine fury | 4
Flower variant 1 | 1 |  | UVing | 4 | [7 empty] | Boss fight music | 5 | [7 empty] | Dodge | 4
Flower variant 2 | 1 |  | Baking | 2 | [7 empty] | Movement | 3
Flower variant 3 | 1 |  | Texturing | 13 | [7 empty] | Snarling | 3 | [7 empty] | Villagers | 8
Flower variant 4 | 1 |  | Rigging | 13 | [7 empty] | Staggered | 3 | [7 empty] | Idle | 3
Flower variant 5 | 1 | [19 empty] | Walk | 3
Flower variant 6 | 1 |  | Hunters | [8 empty] | Player | 50 | [7 empty] | Conversing | 2
Grass variant 1 | 1 | [10 empty] | Footsteps | 1
Grass variant 2 | 1 |  | Tikbalang | [8 empty] | Sword swing | 1 | [7 empty] | Tikbalang
Mushroom variant 1 | 1 | [10 empty] | Attack effort | 1 | [7 empty] | Idle
Mushroom variant 2 | 1 | [10 empty] | Sword impact | 1 | [7 empty] | Walking
Fern variant 1 | 1 | [10 empty] | Fireball charging | 3 | [7 empty] | Running
Vines | 2 | [10 empty] | Fireball launching | 3 | [7 empty] | Stagger
Leaf pile | 2 | [10 empty] | Fireball impact | 3 | [7 empty] | Death
Bamboo shoots | 4 | [10 empty] | Earth shield casting | 3 | [7 empty] | Mirror images
Rock variant 1 | 3 | [10 empty] | Earth shield impact | 3 | [7 empty] | Charge attack
Rock variant 2 | 3 | [10 empty] | Earth shield ending | 3 | [7 empty] | Stomp attack
Rock variant 3 | 3 | [10 empty] | Earth shield healing | 3 | [7 empty] | Shield slam
Rock variant 4 | 3 | [10 empty] | Imbue cast | 3 | [7 empty] | Spear thrust
Rock variant 5 | 4 | [10 empty] | Imbue persist | 3 | [7 empty] | Spear swipe 1
Rock variant 6 | 4 | [10 empty] | Imbue impact | 3 | [7 empty] | Spear swipe 2
Rock variant 7 | 4 | [10 empty] | Imbue energy waves | 3
Rock archway | 4 | [10 empty] | Imbue wave impact | 3
Moss variant 1 | 1 | [10 empty] | Imbue ending | 3
Moss variant 2 | 1 | [10 empty] | Imbue DoT | 3
[12 empty] | Death | 2
Village Assets | 31 | [10 empty] | Damage Taken | 2
Hut variant 1 | 3
Hut variant 2 | 3
Hut variant 3 | 3
Hut variant 4 | 3
Chapel | 3
Hut destroyed variant 1 | 2
Hut destroyed variant 2 | 2
Hut destroyed variant 3 | 2
Water well | 1.5
Fire torch | 1
Ladder | 1
Bench/table | 1
Wooden fence | 1
Wooden bridge | 2
Wooden Planks | 1.5
Bat | 1
Designer Materials | 39
4 Tree Variants | 13
Dirt | 4
Grass | 4
Stone | 4
Rainbow Tree | 5
Moss | 4
Thatch | 5
Tikbalang Arena | 10
Colonial Town | 50